## Read Me
KPI Tracker: how this sheet works
Built and refreshed by KPI Copilot 2.1.0. Every run updates this same sheet; what you typed in yellow cells is read back first and kept.
Tabs
Dashboard: totals per period and KPI results with coloured bars. Nothing to type here.
Config: project details, counting rules, KPI targets, and the project dates used when a period or task has none.
Periods: one row per KPI period with its dates, notes and PMS period ID.
Task Register: every planned task and additional request, with the evidence behind each Yes/No.
Defect Register: every bug, observation or improvement, including rejected ones.
KPI Summary: the nine PMS KPIs per period, the facts behind each number, your reason, and the note that goes to PMS.
Open Questions: what the sources could not answer. Answer in the yellow cell; the next run keeps it.
Run Log: which sources this run read, which it did not, and how long it took.
PMS Push Log: what was sent to PMS and when.
How to read and change it
Yellow cells are yours: change one and every formula follows at once. The next run reads your change back and keeps it - it is never overwritten.
White cells were read from the tracker, the plan or the estimates. Grey cells are worked out. Editing either achieves nothing; the next run rebuilds them.
The Check column says how a row was decided when it was not obvious: a tag read tolerantly ('read [Exisiting] as Existing'), a loose match to the plan, a call an assistant made and why. Disagree by changing the yellow cell.
Dates: a date on the task wins, then the period date, then the project date in Config. Leave a cell empty to use the next level.
Client date check (Periods or Config): Handover = the build reached the client by the date; Delivery = the item was delivered by the date.
'Since the last run' on KPI Summary speaks up when the sheet's live number no longer matches what the run computed. Run again before anything goes to PMS: PMS always receives what the run computed, never what was typed.
To set a KPI value by hand, use 'Set value by hand' with a reason. Both figures are kept and the note says a person recorded a different one.
Note format sent to PMS
What the numbers say, in sentences ¦¦ what was left out ¦¦ why (your reason). Links never go to PMS; they live here, on the rows.
Period names
Initial Scope, Additional Requests 1, 2 ..., Milestone 1, 2 ..., Full Project (25 characters at most).

## Dashboard
Work and issues by period
# | Period | Delivered | Not delivered yet | Planned tasks | Additional requests | Completed | Issues reported | Bugs counted | Rejected | Found after handover | Reopened | Client date | Commit date | Handed over | Delivered (green) vs not yet (grey) | Bugs (red) vs other issues (orange)
Total
KPI results by period (the bar is green when the KPI is met, red when not)
| KPI | Target
Velocity
Task Comprehension
Client Expectation
Delivery Commitment
Defect Rate
Escaped Defect Rate
Defect Rejection Rate
Rework Rate
CR Rate
Status across all periods
| Met |  | Not met
| Not measured yet |  | Reasons still missing
| Rows waiting for a check |  | Open questions
What moved since the last run: nothing

## Config
KPI Tracker - Configuration
Yellow cells are settings the sheet's formulas read. The run reads them back: dates are kept; a counting rule changed here is reported and asked about, never applied quietly.
PROJECT
| Project name | Acme Demo Identity
Client
| PMS project ID | 201
PMS KPI page
| Issue tracker | Jira
| Tracker board | Open
| Engagement type | Project
| Period type | Sprint
| Sources read | Issue tracker
| Deliverables are counted as | Board cards (one card, one deliverable)
| Calculated as of | 2026-09-18
| Prepared by | Sample Lead
COUNTING RULES
| Velocity unit | Story Points | What Velocity adds up for delivered tasks and additional requests.
| Hours counted in Velocity | Dev only | Dev + QA adds an item's QA hours once the item is closed.
| Count observations as defects? | No | No = only Bug rows count in Defect Rate.
| Count improvements as defects? | No
| Count pre-existing defects in Defect Rate? | No | Pre-existing = already in the product before this work.
| Count post-release defects in Defect Rate? | Yes | Post-release defects always count in Escaped Defect Rate.
| A commitment is met on | Delivery | Delivery = the item reached its delivery event by the date. Handover = the build reached the client by it.
| CR Rate is measured against | This period | A period made only of additional requests is always measured against the whole project.
KPI TARGETS (source and any local review override are shown beside each target)
| KPI | Unit | PMS KPI ID | Type | Target | Formula (PMS definition) | How this sheet counts it | Target comes from
| Velocity | Per Config | 9 | Min | 10 | Total work completed in the period (story points / hours). | Hours (or story points) of Task Register rows that are not Excluded and have a Delivered date, plus the period's team-level effort. | bundled fallback, not read from PMS
| Task Comprehension | % | 1 | Min | 80 | Understood task count / Total task count | Rows with Understood = Yes ÷ rows with Understood = Yes or No. A row with no answer is left out. | bundled fallback, not read from PMS
| Client Expectation | % | 2 | Min | 90 | On-time delivered (client-expected) / Total client-expected tasks | Client-expected rows that met their date ÷ client-expected rows that are due. Pending rows wait. | bundled fallback, not read from PMS
| Delivery Commitment | % | 4 | Min | 100 | Delivered on time (committed) / Total team-committed tasks | Rows the team committed to that met the date ÷ committed rows that are due. Uncommitted rows are left out. | bundled fallback, not read from PMS
| Defect Rate | % | 5 | Max | 15 | Number of defects found / Total task count | Defect Register rows with Counts in Defect Rate = Yes ÷ delivered Task Register rows. | bundled fallback, not read from PMS
| Escaped Defect Rate | % | 8 | Max | 5 | Defects found after release / Total defects (before + after release) | Post-release reports that were not rejected ÷ all reports that were not rejected. Blank until the period is handed over. | bundled fallback, not read from PMS
| Defect Rejection Rate | % | 7 | Max | 15 | Rejected defects / Total reported defects | Defect Register rows with Rejected = Yes ÷ all Defect Register rows. | bundled fallback, not read from PMS
| Rework Rate | % | 6 | Max | 10 | Tasks reopened / Total tasks completed | Reopening events after the configured close boundary ÷ completed rows assessed for rework. | bundled fallback, not read from PMS
| CR Rate | % | 3 | Max | 20 | CR count / Initial task count | Rows with Item Type = CR ÷ rows with Item Type = Task (the whole project's, when the period has none). | bundled fallback, not read from PMS
PROJECT DATES (used when a period or a task has no date of its own)
| Client expected date |  | What the client expects: the planned handover, a client deadline, or a date agreed again after the client added work.
| Team commitment date |  | What the team agreed to deliver by: the milestone date or a date negotiated later.
| Client date check | Handover | Handover = met when the build reached the client by the date. Delivery = met when the item itself was delivered by it.
| Why these dates |  | Short reason, with where it was agreed.

## Periods
Periods
One row per KPI period. Leave a date empty to use the project date from Config.
# | Period Name (max 25) | Start | End | PMS Description (auto) | Client Expected Date | Commitment Date | Handed Over On | PMS Period ID | Pushed to PMS On | Notes | Original Plan | Team-level Effort (h) | Client Date Check
| Sprint 14 |  |  | 4 planned tasks + 1 additional request
| Sprint 15 |  |  | 2 planned tasks

## Task Register
Task Register (9 rows)
Every planned task and additional request, plus excluded cards so nothing looks missing. Yellow = you can change it; grey = worked out by formula; Check says how a row was decided.
# | Period | Ticket | Link | Title | Item Type | Planned (initial scope)? | Est. Hours (counted) | Story Points | Hours Source | Assignee | Created | Delivered | Closed | Status | Understood w/o Client? | Comprehension Evidence | Comprehension Link | Client-Expected? | Client Expected Date | Met Client Date? | Team Committed? | Commitment Date | Met Commitment? | Reopened after closing? | Reopening Events | Rework Evidence | Rework Link | Remarks and sources | Dev Hours | QA Hours | Board Column | Check (how this row was decided) | Period handover | Client date check | Row ID | Delivery evidence missing | Group estimate only | Estimate held on group | Group estimate not yet delivered | Required estimate missing | Rework close boundary
| Sprint 14 | ACME-101 | Open | Single sign-on for the portal | Task | Yes |  | 8 | Tracker estimate | Sample Developer A | 2026-08-03 | 2026-08-21 | 2026-08-21 |  |  |  |  | No |  |  | No | [7 empty] | 32 |  | Done |  |  |  |  | No | No | No group |  |  | 2026-08-21
| Sprint 14 | ACME-102 | Open | Audit log export | Task | Yes |  | 5 | Tracker estimate | Sample Developer B | 2026-08-03 | 2026-08-25 | 2026-08-25 |  |  |  |  | No |  |  | No | [7 empty] | 18 |  | Done |  |  |  |  | No | No | No group |  |  | 2026-08-25
| Sprint 14 | ACME-103 | Open | Role editor screen | Task | Yes |  | 8 | Tracker estimate | Sample Developer A | 2026-08-04 | 2026-08-27 | 2026-08-27 |  |  |  |  | No |  |  | No | [7 empty] | 24 |  | Done |  |  |  |  | No | No | No group |  |  | 2026-08-27
| Sprint 14 | ACME-104 | Open | Bulk user import | Task | Yes |  | 5 | Tracker estimate | Sample Developer C | 2026-08-05 | [6 empty] | No |  |  | No | [7 empty] | 20 |  | In Progress |  |  |  |  | No | No | No group
| Sprint 14 | ACME-110 | Open | Sprint Goal: identity work | Excluded |  |  |  | Tracker estimate | PM | 2026-08-03 | 2026-08-28 | 2026-08-28 | [14 empty] | Title matches the team's 'not a deliverable' rule (^Sprint Goal) | 0 |  | Done |  |  |  |  | No | No | No group |  |  | 2026-08-28
| Sprint 14 | ACME-111 | Open | QA Checklist Sprint 14 | Excluded |  |  |  | Tracker estimate | QA Lead | 2026-08-03 | 2026-08-28 | 2026-08-28 | [14 empty] | Title matches the team's 'not a deliverable' rule (^QA Checklist) | 0 |  | Done |  |  |  |  | No | No | No group |  |  | 2026-08-28
| Sprint 14 | ACME-120 | Open | SSO session timeout configurable | CR | No |  | 3 | Tracker estimate | Sample Developer B | 2026-08-14 | 2026-08-26 | 2026-08-26 |  |  |  |  | No |  |  | No | [7 empty] | 10 |  | Done |  |  |  |  | No | No | No group |  |  | 2026-08-26
| Sprint 15 | ACME-201 | Open | Delegated admin roles | Task | Yes |  | 8 | Tracker estimate | Sample Developer C | 2026-09-01 | [6 empty] | No |  |  | No | [7 empty] | 28 |  | In Progress |  |  |  |  | No | No | No group
| Sprint 15 | ACME-202 | Open | Session revocation API | Task | Yes |  | 5 | Tracker estimate | Sample Developer B | 2026-09-01 | 2026-09-15 | 2026-09-15 |  |  |  |  | No |  |  | No | [7 empty] | 16 |  | Done |  |  |  |  | No | No | No group |  |  | 2026-09-15

## Defect Register
Defect Register (5 rows)
Every bug, observation or improvement reported by QA or the client, including rejected ones.
# | Period | Ticket | Link | Title | Kind | Reported By | Reported On | Phase | Pre-existing? | Rejected? | Rejection Reason | Evidence | Final Status | Counts in Defect Rate? | Remarks and sources | Check (how this row was decided) | Row ID
| Sprint 14 | ACME-131 | Open | SSO redirect loops on Safari | Bug | QA Lead | 2026-08-18 | Pre-release |  | No | Fixed | Open
| Sprint 14 | ACME-132 | Open | Audit export misses deleted users | Bug | QA Lead | 2026-08-19 | Pre-release |  | No | Fixed | Open
| Sprint 14 | ACME-133 | Open | Role editor spacing looks off | Improvement | QA Lead | 2026-08-20 | Pre-release |  | No | Done | Open
| Sprint 14 | ACME-134 | Open | Cannot log in at all | Bug | QA Lead | 2026-08-21 | Pre-release |  | Yes | Cannot Reproduce | Open
| Sprint 15 | ACME-135 | Open | SSO fails for federated domain | Bug | Client PM | 2026-09-02 | Post-release |  |  |  | Open

## KPI Summary
KPI Summary
Edit either yellow note column. The result summary starts with suggested wording; your edits are kept. The PMS note combines the summary and context. Review items stay on Open Questions. Every push reads this sheet again before preparing the values and notes.
Period | # | KPI | PMS KPI ID | Numerator | Denominator | Value | Target | Min / Max | Status | Needs a reason? | Result summary (editable) | Why / context (editable) | Note sent to PMS (auto, no links) | Computed by the run | Since the last run | Set value by hand | Why set by hand
Sprint 14 | 1 | Velocity | [8 empty] | Delivered work represents 24 story points in this cycle, across 4 delivered items: 3 from the plan and 1 additional request. ¦¦ 1 more item is still in progress. |  |  | 24
Sprint 14 | 2 | Task Comprehension
Sprint 14 | 3 | Client Expectation
Sprint 14 | 4 | Delivery Commitment
Sprint 14 | 5 | Defect Rate | [8 empty] | 2 defects were reported against 4 delivered tickets. That is 50 defects per 100 delivered tickets (50%). One ticket can have several defects, so this is not the percentage of tickets with a problem. ¦¦ Another 2 reports were not counted: 1 improvement and 1 closed as not a bug. |  |  | 50
Sprint 14 | 6 | Escaped Defect Rate
Sprint 14 | 7 | Defect Rejection Rate | [8 empty] | 1 of the 4 reports turned out not to be a bug (25%). ¦¦ It was closed as cannot reproduce. |  |  | 25
Sprint 14 | 8 | Rework Rate
Sprint 14 | 9 | CR Rate | [8 empty] | The client added 1 request on top of the 4 planned items (25%). |  |  | 25
Sprint 15 | 1 | Velocity | [8 empty] | Delivered work represents 5 story points in this cycle, across 1 delivered item. ¦¦ 1 more item is still in progress. |  |  | 5
Sprint 15 | 2 | Task Comprehension
Sprint 15 | 3 | Client Expectation
Sprint 15 | 4 | Delivery Commitment
Sprint 15 | 5 | Defect Rate | [8 empty] | 1 defect was reported against 1 delivered ticket. That is 100 defects per 100 delivered tickets (100%). One ticket can have several defects, so this is not the percentage of tickets with a problem. |  |  | 100
Sprint 15 | 6 | Escaped Defect Rate
Sprint 15 | 7 | Defect Rejection Rate | [8 empty] | None of the 1 report was rejected. |  |  | 0
Sprint 15 | 8 | Rework Rate
Sprint 15 | 9 | CR Rate | [8 empty] | The client added no extra work to this cycle. The plan holds 2 planned items (0%). |  |  | 0

## Open Questions
Open Questions
What the sources on file could not answer. Type the answer in the yellow cell; the next run reads it, keeps it, and stops asking. Nothing here was guessed - an unanswered row is left out of the numbers.
# | About | Question | If nobody answers | Your answer | Asked on | ID
| Sprint 14 · Task Comprehension | Review this measurement: Nothing to measure: none of the 5 items carries the evidence this needs, so nothing could be judged either way. |  |  | 2026-09-18 | review:Sprint 14¦Task Comprehension:ca215ed6aa7b
| Sprint 14 · Task Comprehension | Review this measurement: The tracker adapter could not read status history, so this is based only on what was filled in by hand. |  |  | 2026-09-18 | review:Sprint 14¦Task Comprehension:db1a683496ee
| Sprint 14 · Client Expectation | Review this measurement: Nothing to measure: none of the 5 items carries the evidence this needs, so nothing could be judged either way. |  |  | 2026-09-18 | review:Sprint 14¦Client Expectation:ca215ed6aa7b
| Sprint 14 · Delivery Commitment | Review this measurement: No team commitment was recorded against any of the 5 items in this cycle, so there is nothing to measure reliability against. |  |  | 2026-09-18 | review:Sprint 14¦Delivery Commitment:32388f0ddfca
| Sprint 14 · Delivery Commitment | Review this measurement: The tracker adapter could not read status history, so whether a commitment was met is based only on what was filled in by hand. |  |  | 2026-09-18 | review:Sprint 14¦Delivery Commitment:a006e91afa65
| Sprint 14 · Escaped Defect Rate | Review this measurement: A client handover has not been recorded, so defects found after handover cannot be measured yet. |  |  | 2026-09-18 | review:Sprint 14¦Escaped Defect Rate:22581d6d8ed6
| Sprint 14 · Escaped Defect Rate | Review this measurement: A client handover date is not recorded, so escaped defects cannot be assessed yet. |  |  | 2026-09-18 | review:Sprint 14¦Escaped Defect Rate:d96b991cda8a
| Sprint 14 · Rework Rate | Review this measurement: None of the 4 completed tasks records whether it was reopened after closing, so there is nothing to measure. |  |  | 2026-09-18 | review:Sprint 14¦Rework Rate:b9f992ddcf7c
| Sprint 14 · Rework Rate | Review this measurement: The adapter cannot see status history, so a reopen is only detected where it was recorded by hand. |  |  | 2026-09-18 | review:Sprint 14¦Rework Rate:cc44c795eb89
| Sprint 15 · Task Comprehension | Review this measurement: Nothing to measure: none of the 2 items carries the evidence this needs, so nothing could be judged either way. |  |  | 2026-09-18 | review:Sprint 15¦Task Comprehension:cf1718f2d6fa
| Sprint 15 · Task Comprehension | Review this measurement: The tracker adapter could not read status history, so this is based only on what was filled in by hand. |  |  | 2026-09-18 | review:Sprint 15¦Task Comprehension:db1a683496ee
| Sprint 15 · Client Expectation | Review this measurement: Nothing to measure: none of the 2 items carries the evidence this needs, so nothing could be judged either way. |  |  | 2026-09-18 | review:Sprint 15¦Client Expectation:cf1718f2d6fa
| Sprint 15 · Delivery Commitment | Review this measurement: No team commitment was recorded against any of the 2 items in this cycle, so there is nothing to measure reliability against. |  |  | 2026-09-18 | review:Sprint 15¦Delivery Commitment:42a5b0b4eef3
| Sprint 15 · Delivery Commitment | Review this measurement: The tracker adapter could not read status history, so whether a commitment was met is based only on what was filled in by hand. |  |  | 2026-09-18 | review:Sprint 15¦Delivery Commitment:a006e91afa65
| Sprint 15 · Escaped Defect Rate | Review this measurement: A client handover has not been recorded, so defects found after handover cannot be measured yet. |  |  | 2026-09-18 | review:Sprint 15¦Escaped Defect Rate:22581d6d8ed6
| Sprint 15 · Escaped Defect Rate | Review this measurement: A client handover date is not recorded, so escaped defects cannot be assessed yet. |  |  | 2026-09-18 | review:Sprint 15¦Escaped Defect Rate:d96b991cda8a
| Sprint 15 · Rework Rate | Review this measurement: None of the 1 completed task records whether it was reopened after closing, so there is nothing to measure. |  |  | 2026-09-18 | review:Sprint 15¦Rework Rate:6c483485a374
| Sprint 15 · Rework Rate | Review this measurement: The adapter cannot see status history, so a reopen is only detected where it was recorded by hand. |  |  | 2026-09-18 | review:Sprint 15¦Rework Rate:cc44c795eb89

## Run Log
Run Log
What this run read, what it deliberately did not, and how long it took. A run reads the sources on this list and nothing else; anything they could not answer is on the Open Questions tab.
# | Source | State | As of | Note
1 | issue tracker | adapter |  | read by the tracker's own adapter
2 | chat, mail, other documents | not read |  | Outside this run's sources. Add one to the profile, or ask for a deep run, to include it.
This run
| Run on | 2026-09-18
| Tool version | 2.1.0
| Source-of-truth mode | tracker-only
| Cards read | 0
| Judged by an assistant or a person (kept) | 0
| Waiting for an assistant | 0
| Waiting for a person | 18

## PMS Push Log
PMS Push Log
One line each time values are sent to PMS. Added by the push.
# | Pushed On | Period | PMS Period ID | Action | What changed | Note or pushed by | Result