## Read Me
KPI Tracker: how this sheet works
Built and refreshed by KPI Copilot 2.1.0. Every run updates this same sheet; what you typed in yellow cells is read back first and kept.
Tabs
Dashboard: totals per period and KPI results with coloured bars. Nothing to type here.
Config: project details, counting rules, KPI targets, and the project dates used when a period or task has none.
Periods: one row per KPI period with its dates, notes and PMS period ID.
Task Register: every planned task and additional request, with the evidence behind each Yes/No.
Defect Register: every bug, observation or improvement, including rejected ones.
KPI Summary: the nine PMS KPIs per period, the facts behind each number, your reason, and the note that goes to PMS.
Open Questions: what the sources could not answer. Answer in the yellow cell; the next run keeps it.
Run Log: which sources this run read, which it did not, and how long it took.
PMS Push Log: what was sent to PMS and when.
How to read and change it
Yellow cells are yours: change one and every formula follows at once. The next run reads your change back and keeps it - it is never overwritten.
White cells were read from the tracker, the plan or the estimates. Grey cells are worked out. Editing either achieves nothing; the next run rebuilds them.
The Check column says how a row was decided when it was not obvious: a tag read tolerantly ('read [Exisiting] as Existing'), a loose match to the plan, a call an assistant made and why. Disagree by changing the yellow cell.
Dates: a date on the task wins, then the period date, then the project date in Config. Leave a cell empty to use the next level.
Client date check (Periods or Config): Handover = the build reached the client by the date; Delivery = the item was delivered by the date.
'Since the last run' on KPI Summary speaks up when the sheet's live number no longer matches what the run computed. Run again before anything goes to PMS: PMS always receives what the run computed, never what was typed.
To set a KPI value by hand, use 'Set value by hand' with a reason. Both figures are kept and the note says a person recorded a different one.
Note format sent to PMS
What the numbers say, in sentences ¦¦ what was left out ¦¦ why (your reason). Links never go to PMS; they live here, on the rows.
Period names
Initial Scope, Additional Requests 1, 2 ..., Milestone 1, 2 ..., Full Project (25 characters at most).

## Dashboard
Work and issues by period
# | Period | Delivered | Not delivered yet | Planned tasks | Additional requests | Completed | Issues reported | Bugs counted | Rejected | Found after handover | Reopened | Client date | Commit date | Handed over | Delivered (green) vs not yet (grey) | Bugs (red) vs other issues (orange)
Total
KPI results by period (the bar is green when the KPI is met, red when not)
| KPI | Target
Velocity
Task Comprehension
Client Expectation
Delivery Commitment
Defect Rate
Escaped Defect Rate
Defect Rejection Rate
Rework Rate
CR Rate
Status across all periods
| Met |  | Not met
| Not measured yet |  | Reasons still missing
| Rows waiting for a check |  | Open questions
What moved since the last run: nothing

## Config
KPI Tracker - Configuration
Yellow cells are settings the sheet's formulas read. The run reads them back: dates are kept; a counting rule changed here is reported and asked about, never applied quietly.
PROJECT
| Project name | Northwind Demo Release
Client
| PMS project ID | 101
PMS KPI page
| Issue tracker | Asana
| Tracker board | Open
| Engagement type | Project
| Period type | Delivery cycle
| Sources read | Issue tracker, Estimates, Timeline
| Deliverables are counted as | Board cards (one card, one deliverable)
| Calculated as of | 2026-09-18
| Prepared by | Project Lead
COUNTING RULES
| Velocity unit | Estimated Hours | What Velocity adds up for delivered tasks and additional requests.
| Hours counted in Velocity | Dev + QA | Dev + QA adds an item's QA hours once the item is closed.
| Count observations as defects? | No | No = only Bug rows count in Defect Rate.
| Count improvements as defects? | No
| Count pre-existing defects in Defect Rate? | No | Pre-existing = already in the product before this work.
| Count post-release defects in Defect Rate? | Yes | Post-release defects always count in Escaped Defect Rate.
| A commitment is met on | Delivery | Delivery = the item reached its delivery event by the date. Handover = the build reached the client by it.
| CR Rate is measured against | This period | A period made only of additional requests is always measured against the whole project.
KPI TARGETS (source and any local review override are shown beside each target)
| KPI | Unit | PMS KPI ID | Type | Target | Formula (PMS definition) | How this sheet counts it | Target comes from
| Velocity | Per Config | 9 | Min | 10 | Total work completed in the period (story points / hours). | Hours (or story points) of Task Register rows that are not Excluded and have a Delivered date, plus the period's team-level effort. | bundled fallback, not read from PMS
| Task Comprehension | % | 1 | Min | 80 | Understood task count / Total task count | Rows with Understood = Yes ÷ rows with Understood = Yes or No. A row with no answer is left out. | bundled fallback, not read from PMS
| Client Expectation | % | 2 | Min | 90 | On-time delivered (client-expected) / Total client-expected tasks | Client-expected rows that met their date ÷ client-expected rows that are due. Pending rows wait. | bundled fallback, not read from PMS
| Delivery Commitment | % | 4 | Min | 100 | Delivered on time (committed) / Total team-committed tasks | Rows the team committed to that met the date ÷ committed rows that are due. Uncommitted rows are left out. | bundled fallback, not read from PMS
| Defect Rate | % | 5 | Max | 15 | Number of defects found / Total task count | Defect Register rows with Counts in Defect Rate = Yes ÷ delivered Task Register rows. | bundled fallback, not read from PMS
| Escaped Defect Rate | % | 8 | Max | 5 | Defects found after release / Total defects (before + after release) | Post-release reports that were not rejected ÷ all reports that were not rejected. Blank until the period is handed over. | bundled fallback, not read from PMS
| Defect Rejection Rate | % | 7 | Max | 15 | Rejected defects / Total reported defects | Defect Register rows with Rejected = Yes ÷ all Defect Register rows. | bundled fallback, not read from PMS
| Rework Rate | % | 6 | Max | 10 | Tasks reopened / Total tasks completed | Reopening events after the configured close boundary ÷ completed rows assessed for rework. | bundled fallback, not read from PMS
| CR Rate | % | 3 | Max | 20 | CR count / Initial task count | Rows with Item Type = CR ÷ rows with Item Type = Task (the whole project's, when the period has none). | bundled fallback, not read from PMS
PROJECT DATES (used when a period or a task has no date of its own)
| Client expected date | 2026-09-11 | What the client expects: the planned handover, a client deadline, or a date agreed again after the client added work.
| Team commitment date | 2026-09-11 | What the team agreed to deliver by: the milestone date or a date negotiated later.
| Client date check | Delivery | Handover = met when the build reached the client by the date. Delivery = met when the item itself was delivered by it.
| Why these dates | Northwind's Q3 feature freeze is 09/11. No new features after it; bug fixes are allowed until 09/25. | Short reason, with where it was agreed.

## Periods
Periods
One row per KPI period. Leave a date empty to use the project date from Config.
# | Period Name (max 25) | Start | End | PMS Description (auto) | Client Expected Date | Commitment Date | Handed Over On | PMS Period ID | Pushed to PMS On | Notes | Original Plan | Team-level Effort (h) | Client Date Check
| Initial Scope | 2026-07-01 | 2026-08-12 | 07/01 to 08/12, 7 planned tasks + 2 Additional Requests, handed over 08/12 |  |  | 2026-08-12 | 501 |  | The planned work plus the additions approved on 07/31 and 08/10, handed over together. | Build to QA 07/20, handover 07/29 (plan). | 40
| Additional Requests 1 | 2026-08-27 | 2026-09-30 | 08/27 to 09/30, 2 Additional Requests |  |  |  | 502 |  | The two additional requests approved on 08/28. | Handover 09/16 (timeline).

## Task Register
Task Register (15 rows)
Every planned task and additional request, plus excluded cards so nothing looks missing. Yellow = you can change it; grey = worked out by formula; Check says how a row was decided.
# | Period | Ticket | Link | Title | Item Type | Planned (initial scope)? | Est. Hours (counted) | Story Points | Hours Source | Assignee | Created | Delivered | Closed | Status | Understood w/o Client? | Comprehension Evidence | Comprehension Link | Client-Expected? | Client Expected Date | Met Client Date? | Team Committed? | Commitment Date | Met Commitment? | Reopened after closing? | Reopening Events | Rework Evidence | Rework Link | Remarks and sources | Dev Hours | QA Hours | Board Column | Check (how this row was decided) | Period handover | Client date check | Row ID | Delivery evidence missing | Group estimate only | Estimate held on group | Group estimate not yet delivered | Required estimate missing | Rework close boundary
| Initial Scope | NW-101 | Open | NW-101 Booking rules for shared rooms | Task | Yes |  |  | Project plan: dev 26.5 + QA 8 | Sample Developer | 2026-06-19 | 2026-07-16 | 2026-08-05 |  | No | went to 'Awaiting Feedback' on 07/08 | Open | Yes | 2026-09-11 |  | Yes | 2026-09-11 |  | No | 0 | Failed QA on 07/22 while still being tested for the first time, so it is not counted as rework (the task was never closed and reopened) |  | Plan: Milestone 1. Original plan: 07/29 | 26.5 | 8 | Closed | understood: went to 'Awaiting Feedback' on 07/08 (not confirmed) |  |  | 1200000000000001 | No | No | No group |  |  | 2026-08-05
| Initial Scope | NW-102 | Open | NW-102 Conflict warning on double booking | Task | Yes |  |  | Project plan: dev 21.5 + QA 6 | Sample Developer | 2026-06-19 | 2026-07-14 | 2026-08-05 |  | Yes |  |  | Yes | 2026-09-11 |  | Yes | 2026-09-11 |  | No | 0 |  |  | Plan: Milestone 1. Original plan: 07/29 | 21.5 | 6 | Closed |  |  |  | 1200000000000002 | No | No | No group |  |  | 2026-08-05
| Initial Scope | NW-103 | Open | NW-103 Richer confirmation email template | Task | Yes |  |  | Project plan: dev 41 + QA 10 | Sample Developer | 2026-06-20 | 2026-07-20 | 2026-08-05 |  | Yes |  |  | Yes | 2026-09-11 |  | Yes | 2026-09-11 |  | No | 0 | Failed QA on 07/23 while still being tested for the first time, so it is not counted as rework (the task was never closed and reopened) |  | Plan: Milestone 2. Original plan: 07/29 | 41 | 10 | Closed |  |  |  | 1200000000000003 | No | No | No group |  |  | 2026-08-05
| Initial Scope | NW-104 | Open | NW-104 Remember the last used filter | Task | Yes |  |  | Project plan: dev 3.5 + QA 2 | Sample Developer | 2026-06-20 | 2026-07-13 | 2026-08-11 |  | Yes |  |  | Yes | 2026-09-11 |  | Yes | 2026-09-11 |  | Yes | 1 | Closed on 08/04 and reopened on 08/07 | Open | Plan: Milestone 1. Original plan: 07/29 | 3.5 | 2 | Closed |  |  |  | 1200000000000004 | No | No | No group |  |  | 2026-08-11
| Initial Scope | NW-105 | Open | NW-105 Export bookings to CSV | Task | Yes |  |  | Project plan: dev 10 + QA 2 | Sample Developer | 2026-06-21 | 2026-07-17 | 2026-08-05 |  | Yes |  |  | Yes | 2026-09-11 |  | Yes | 2026-09-11 |  | No | 0 |  |  | Plan: Milestone 1. Original plan: 07/29 | 10 | 2 | Closed | understood: waited in 'Awaiting Feedback' on 07/10, but for environment, not for the requirement (not confirmed) |  |  | 1200000000000005 | No | No | No group |  |  | 2026-08-05
| Initial Scope | NW-106 | Open | NW-106 Tablet check-in screen | Task | Yes |  |  | Project plan: dev 33.5 + QA 6 | Sample Developer | 2026-06-22 | 2026-07-28 |  |  | Yes |  |  | Yes | 2026-09-11 |  | Yes | 2026-09-11 | [5 empty] | Plan: Milestone 2. Original plan: 07/29 | 33.5 | 6 | Ready for QA |  |  |  | 1200000000000006 | No | No | No group
| Initial Scope | NW-140 | Open | [CR] NW-140 Single sign-on fix | CR | No |  |  | Estimates sheet: dev 10 + QA 4 | Sample Developer | 2026-07-30 | 2026-08-06 | 2026-08-11 |  | Yes |  |  | Yes | 2026-09-11 |  | Yes | 2026-09-11 |  | No | 0 |  |  | Approved 07/31. Original plan: 07/29 | 10 | 4 | Closed |  |  |  | 1200000000000007 | No | No | No group |  |  | 2026-08-11
| Initial Scope | NW-141 | Open | NW-141 Extra fields on the room profile | CR | No |  |  | Estimates sheet: dev 14 + QA 4 | Sample Developer | 2026-08-10 | 2026-08-11 | 2026-08-12 |  | Yes |  |  | Yes | 2026-09-11 |  | Yes | 2026-09-11 |  | No | 0 |  |  | Approved 08/10. Original plan: 07/29 | 14 | 4 | Closed |  |  |  | 1200000000000008 | No | No | No group |  |  | 2026-08-12
| Additional Requests 1 | NW-160 | Open | NW-160 Calendar sync for cancelled bookings | CR | No |  |  | Estimates sheet: dev 32 + QA 8 | Sample Developer | 2026-08-28 | 2026-09-10 |  |  | Yes |  |  | Yes | 2026-09-11 |  | Yes | 2026-09-11 | [5 empty] | Approved 08/28. Original plan: 09/16 | 32 | 8 | Ready for QA |  |  |  | 1200000000000009 | No | No | No group
| Additional Requests 1 | NW-161 | Open | [CRs] NW-161 Reminder emails before a booking | CR | No |  |  | Estimates sheet: dev 24 + QA 6 | Sample Developer | 2026-08-28 | 2026-09-08 | 2026-09-15 |  | Yes |  |  | Yes | 2026-09-11 |  | Yes | 2026-09-11 |  | No | 0 |  |  | Approved 08/28. Original plan: 09/16 | 24 | 6 | Closed |  |  |  | 1200000000000010 | No | No | No group |  |  | 2026-09-15
| Initial Scope | NW-150 | Open | NW-150 Tidy up tablet log noise | Scope | No |  |  |  | Sample Developer | 2026-08-03 | 2026-08-05 | 2026-08-06 |  | Yes |  |  | Yes | 2026-09-11 |  | Yes | 2026-09-11 |  | No | 0 |  |  | Original plan: 07/29 |  |  | Closed | type: on the board but in neither the plan nor the approved additions (not confirmed) |  |  | 1200000000000011 | No | No | No group |  |  | 2026-08-06
| Initial Scope |  | Open | [QA] Checklist for release 4.2 | Excluded |  |  |  |  | Sample Developer | 2026-07-01 |  | 2026-07-01 | [14 empty] | Title matches the exclude pattern ^\[QA\] |  |  | Closed |  |  |  | 1200000000000012 | No | No | No group |  |  | 2026-07-01
| Initial Scope |  | Open | Milestone 1 | Excluded |  |  |  |  | Sample Developer | 2026-06-18 |  | 2026-06-18 | [14 empty] | An Asana milestone marker, not a deliverable |  |  | Closed |  |  |  | 1200000000000013 | No | No | No group |  |  | 2026-06-18
| Initial Scope |  | Open | Regression Testing round 2 | Excluded |  |  |  |  | Sample Developer | 2026-08-06 |  | 2026-08-06 | [14 empty] | Title matches the exclude pattern ^Regression Testing |  |  | Closed |  |  |  | 1200000000000014 | No | No | No group |  |  | 2026-08-06
| Initial Scope | Plan item |  | Delivery documentation | Task | Yes |  |  | Project plan | [8 empty] | Yes | 2026-09-11 |  | Yes | 2026-09-11 | [5 empty] | In the plan with no card of its own on the board | 6 | 0 | Not on the board | no card on the board; delivery date not known |  |  | plan:deliverydocumentation | Yes | No | No group

## Defect Register
Defect Register (11 rows)
Every bug, observation or improvement reported by QA or the client, including rejected ones.
# | Period | Ticket | Link | Title | Kind | Reported By | Reported On | Phase | Pre-existing? | Rejected? | Rejection Reason | Evidence | Final Status | Counts in Defect Rate? | Remarks and sources | Check (how this row was decided) | Row ID
| Initial Scope | Bug 01 | Open | [Web] Bug 01: Warning shown for recurring bookings | Bug | Sample QA | 2026-07-18 | Pre-release | No | No |  | Open | Fixed / Closed |  |  |  | 1200000000000020
| Initial Scope | Bug 02 | Open | [Tablet] Bug 02: Filter lost when the language changes | Bug | Sample QA | 2026-07-19 | Pre-release | No | No |  | Open | Fixed / Closed |  |  |  | 1200000000000021
| Initial Scope | Bug 03 | Open | [Web][Existing] Bug 03: Long room names overlap the next column | Bug | Sample QA | 2026-07-19 | Pre-release | Yes | No |  | Open | Fixed / Closed |  |  |  | 1200000000000022
| Initial Scope | Bug 04 | Open | [Tablet][Exisiting] Bug 04: Button labels cropped on small screens | Bug | Sample QA | 2026-07-21 | Pre-release | Yes | No |  | Open | Fixed / Closed |  |  | read [Exisiting] as Existing | 1200000000000023
| Initial Scope | Observation 05 | Open | [Web] Observation 05: Email subject could name the building | Observation | Sample QA | 2026-07-21 | Pre-release | No | No |  | Open | Fixed / Closed |  |  |  | 1200000000000024
| Initial Scope | Bug 06 | Open | [Web] Bug 06: Confirmation email sent twice | Bug | Sample QA | 2026-07-22 | Pre-release | No | Yes | Rejected | Open | Rejected |  |  |  | 1200000000000025
| Initial Scope | Improvement 07 | Open | [Tablet] Improvement 07: Larger confirm button | Improvement | Sample QA | 2026-07-24 | Pre-release | No | No |  | Open | Open |  |  |  | 1200000000000026
| Initial Scope | Bug 08 | Open | [Web] Bug 08: CSV export ignores the date filter | Bug | Sample Client | 2026-08-20 | Post-release | No | No |  | Open | Fixed / Closed |  |  | period: reported 2026-08-20, after Initial Scope ended and before the next period began (not confirmed) | 1200000000000027
| Initial Scope | Bug 09 | Open | [Web] Bug 09: Export times out for large buildings | Bug | Sample QA | 2026-07-27 | Pre-release | Yes | No |  | Open | Fixed / Closed |  |  | pre existing: its description or comments say 'not related to this release' (not confirmed) | 1200000000000028
| Additional Requests 1 | Bug 10 | Open | [Web] Bug 10: Reminder email shows the wrong room | Bug | Sample QA | 2026-09-09 | Pre-release | No | No |  | Open | Fixed / Closed |  |  |  | 1200000000000029
| Additional Requests 1 | Bug 11 | Open | [Web] Bug 11: Cancelled bookings still shown after sync | Bug | Sample QA | 2026-09-11 | Pre-release | No | No |  | Open | Open |  |  |  | 1200000000000030

## KPI Summary
KPI Summary
Edit either yellow note column. The result summary starts with suggested wording; your edits are kept. The PMS note combines the summary and context. Review items stay on Open Questions. Every push reads this sheet again before preparing the values and notes.
Period | # | KPI | PMS KPI ID | Numerator | Denominator | Value | Target | Min / Max | Status | Needs a reason? | Result summary (editable) | Why / context (editable) | Note sent to PMS (auto, no links) | Computed by the run | Since the last run | Set value by hand | Why set by hand
Initial Scope | 1 | Velocity
Initial Scope | 2 | Task Comprehension | [8 empty] | The team understood 8 of the 9 assessed items without asking the client to explain the requirement (88.89%). | The shared-room booking requirement did not say which booking should take priority. The client clarified that recurring bookings win. The CSV export task was blocked by unavailable staging access, which did not require an explanation of the requirement. |  | 88.89
Initial Scope | 3 | Client Expectation | [8 empty] | All 9 items met the client's agreed deadline, each delivered by 09/11 (100%). ¦¦ The cycle was handed over on 08/12. |  |  | 100
Initial Scope | 4 | Delivery Commitment | [8 empty] | All 9 assessed items met their recorded commitment dates by 09/11, counted on each item's delivery date (100%). |  |  | 100
Initial Scope | 5 | Defect Rate | [8 empty] | 3 defects were reported against 9 delivered tickets. That is 33.33 defects per 100 delivered tickets (33.33%). One ticket can have several defects, so this is not the percentage of tickets with a problem. ¦¦ Another 6 reports were not counted: 3 that were already in the product, 1 observation, 1 improvement and 1 closed as not a bug. | The included reports concern recurring-booking warnings, filter retention and the export date filter. Existing issues, suggestions and the rejected test-harness report remain visible in the register under the agreed exclusions. |  | 33.33
Initial Scope | 6 | Escaped Defect Rate | [8 empty] | The client found 1 of the 8 valid issues after handover (12.5%). ¦¦ The cycle was handed over on 08/12. ¦¦ 1 rejected report is excluded from both counts because it was not accepted as a defect. | After the 08/12 handover, the client reported that the CSV export ignored its date filter. The report was closed on 08/25. |  | 12.5
Initial Scope | 7 | Defect Rejection Rate | [8 empty] | 1 of the 9 reports turned out not to be a bug (11.11%). ¦¦ It was closed as rejected. | The duplicate-email report came from the test harness rather than the product, so it was rejected. The decision is recorded in the report's comment. |  | 11.11
Initial Scope | 8 | Rework Rate | [8 empty] | 1 reopening event was recorded across the 8 completed tasks (12.5%). ¦¦ 2 tasks failed QA while still being tested for the first time. That is normal testing rather than rework, so they are not counted here. ¦¦ Those events affected 1 ticket; each return after another close is counted separately. | The saved-filter task passed QA on 08/04 and reopened on 08/07 when a tablet restart exposed the reset. It returned to closed on 08/11. The other two QA failures occurred before their first closure and remain ordinary testing. |  | 12.5
Initial Scope | 9 | CR Rate | [8 empty] | The client added 2 Additional Requests on top of the 7 planned items (28.57%). | Single sign-on repair and extra room-profile fields were approved on 07/31 and 08/10 in the fictional estimates table. They are recorded as Additional Requests rather than silently added to the original plan. |  | 28.57
Additional Requests 1 | 1 | Velocity | [8 empty] | Delivered work represents 62 estimated hours in this cycle, across 2 delivered items. ¦¦ That is 56 hours of development and 6 hours of QA. | Both development items reached QA. The reminder-email item also completed QA; the calendar-sync item had not, so its QA estimate is not yet credited. |  | 62
Additional Requests 1 | 2 | Task Comprehension | [8 empty] | The team understood all 2 items without asking the client to explain the requirement (100%). |  |  | 100
Additional Requests 1 | 3 | Client Expectation | [8 empty] | All 2 items met the client's agreed deadline, each delivered by 09/11 (100%). ¦¦ The cycle has not been handed over to the client yet. |  |  | 100
Additional Requests 1 | 4 | Delivery Commitment | [8 empty] | All 2 assessed items met their recorded commitment dates by 09/11, counted on each item's delivery date (100%). |  |  | 100
Additional Requests 1 | 5 | Defect Rate | [8 empty] | 2 defects were reported against 2 delivered tickets. That is 100 defects per 100 delivered tickets (100%). One ticket can have several defects, so this is not the percentage of tickets with a problem. | The reports concern a wrong room in a reminder email and cancelled bookings remaining after synchronization. The latter remained open at the sample reporting date. |  | 100
Additional Requests 1 | 6 | Escaped Defect Rate
Additional Requests 1 | 7 | Defect Rejection Rate | [8 empty] | None of the 2 reports were rejected. |  |  | 0
Additional Requests 1 | 8 | Rework Rate | [8 empty] | The one assessed completed task was not reopened after closing. ¦¦ Each return after another close is counted separately. |  |  | 0
Additional Requests 1 | 9 | CR Rate | [8 empty] | The client added 2 Additional Requests on top of the 7 planned items (28.57%). ¦¦ This cycle is made up only of Additional Requests, so they are measured against the planned items of the whole project. |  |  | 28.57

## Open Questions
Open Questions
What the sources on file could not answer. Type the answer in the yellow cell; the next run reads it, keeps it, and stops asking. Nothing here was guessed - an unanswered row is left out of the numbers.
# | About | Question | If nobody answers | Your answer | Asked on | ID
| Delivery documentation | 'Delivery documentation' is in the plan but has no card on the board. Was it delivered, and on what date? | Leave it as not delivered. |  | 2026-09-18 | scope:deliverydocumentation
| Additional Requests 1 | Additional Requests 1 had a client delivery date of 09/11. When did its build reach the client? It decides Escaped Defect Rate and the client-date check. | Leave it as not handed over yet. |  | 2026-09-18 | handover:Additional Requests 1
| Initial Scope · Velocity | Review this measurement: Velocity is not measured in hours: 1 of 9 delivered items lack the required estimate. |  |  | 2026-09-18 | review:Initial Scope¦Velocity:44f513bea98c
| Initial Scope · Velocity | Review this measurement: Record the missing estimate or finish the group whose estimate cannot be split; blank does not mean zero. |  |  | 2026-09-18 | review:Initial Scope¦Velocity:2dc5ca0234a4
| Initial Scope · Velocity | Review this measurement: Velocity is not measured in hours: 1 of 9 delivered items lack the required estimate. Record the missing estimate or finish the group whose estimate cannot be split; blank does not mean zero. |  |  | 2026-09-18 | review:Initial Scope¦Velocity:ab970eeec24f
| Initial Scope · Task Comprehension | Review this measurement: 1 other item could not be assessed because individual discussion history was unavailable. |  |  | 2026-09-18 | review:Initial Scope¦Task Comprehension:4a614a2dcd40
| Initial Scope · Escaped Defect Rate | Review this measurement: The available record does not establish why testing missed it. |  |  | 2026-09-18 | review:Initial Scope¦Escaped Defect Rate:dd4d174099e2
| Additional Requests 1 · Escaped Defect Rate | Review this measurement: A client handover has not been recorded, so defects found after handover cannot be measured yet. |  |  | 2026-09-18 | review:Additional Requests 1¦Escaped Defect Rate:22581d6d8ed6
| Additional Requests 1 · Escaped Defect Rate | Review this measurement: A client handover date is not recorded, so escaped defects cannot be assessed yet. |  |  | 2026-09-18 | review:Additional Requests 1¦Escaped Defect Rate:d96b991cda8a

## Run Log
Run Log
What this run read, what it deliberately did not, and how long it took. A run reads the sources on this list and nothing else; anything they could not answer is on the Open Questions tab.
# | Source | State | As of | Note
1 | issue tracker | read | 2026-09-18 | 25 cards; history refreshed for 25, reused for 0 unchanged
2 | estimates | fresh | a2c1a8dc38b0d6d0
3 | timeline | fresh | 6d9cb96b34922f52
4 | chat, mail, other documents | not read |  | Outside this run's sources. Add one to the profile, or ask for a deep run, to include it.
This run
| Run on | 2026-09-18
| Tool version | 2.1.0
| Source-of-truth mode | tracker-first
| Cards read | 25
| Judged by an assistant or a person (kept) | 0
| Waiting for an assistant | 6
| Waiting for a person | 9

## PMS Push Log
PMS Push Log
One line each time values are sent to PMS. Added by the push.
# | Pushed On | Period | PMS Period ID | Action | What changed | Note or pushed by | Result